## Sheet1
Phase | Key Activities | Typical Duration (Weeks) | Responsible Party | Deliverables
Design & Specification | Confirm material list, finishes, and mock-up schedule. Align with designer and brand standards. | -2 | Designer / Procurement Team | Finalized FF&E list, design intent package
Shop Drawings & Sample Approval | Prepare detailed shop drawings; submit samples for material, color, and finish approval. | -3 | Factory / FF&E Consultant | Approved shop drawings and material samples
Production & Quality Control | Begin full production after approvals. Monitor progress with 30/60/90% QC inspections. | -2 | Manufacturer / QC Team | QC reports, production photos, and completion notice
Packing, Shipping & Customs | Pack goods with export-grade protection, arrange container loading, prepare CIQ/HS/CO docs. | -1 | Logistics Team / Export Dept. | Shipping documents, packing lists, container loading report
Site Delivery & Installation | Coordinate with site readiness. Label and deliver items per floor plan; perform installation checks. | -2 | Installation Crew / Project Manager | Handover checklist, installation log, sign-off certificate